SPRINT 02 · WORK CHECKLIST

# Finalize and hire

OptiMind Educational Strategies — Gemini Lane Consulting & Acquisitions

Dates · Aug 26 – Sep 15, 2026    Cost · $2,000    Priorities · 7    Steps · 34

The big rock Every SOP and onboarding document is final, and the new specialist walks into a written first week. The SOP and onboarding set stops being a draft. Every open question is answered or explicitly parked, the documents go to Sarah’s Google Drive as final, and the specialist hired Sep 4 starts the following week against a plan that already exists.

Fixed dates in this sprint. Offer goes out Sep 4 · Week One onboarding Sep 8–12 · Decision session with Sarah, week of Aug 31. Priorities 1 and 2 have to land before Sep 4; priority 4 is the onboarding week itself.

The grey line under a step is the document it belongs to, relative to the OptiMind-Dashboard folder — open it there to do the work.

1ST PRIORITY

## Close every open question in the SOP and onboarding set

One working session against a single register of every TBD, placeholder and unresolved decision across the nineteen documents — answered, or explicitly parked with a named owner and date.

☐  A single register lists every open question and outstanding to-do across the SOP and onboarding set, grouped by document, with an owner against each.

OptiMind-Open-Items-Register.html

☐  Sarah has worked through the register in one sitting and given a decision on each item, or parked it with a date.

OptiMind-Open-Items-Register.html

☐  Every parked item is visibly marked in the document itself, so a reader knows it is open rather than assuming it is settled.

☐  The items requiring an attorney (non-compete, mandated-reporter status, EEO thresholds, record retention) are separated out and sent as one bundle, not one at a time.

OptiMind-Offer-Package-Open-Decisions.docx  ·  Sent as the Offer Package — Open Decisions document.

2ND PRIORITY

## Pre-hire paperwork ready to sign by Sep 4

Offer letter, employment agreement and confidentiality agreement carrying real terms — name, start date, compensation, schedule — not placeholders, before the offer goes out.

☐  Compensation structure and amount, pay frequency, schedule and start date are decided and written into the Offer Letter and Employment Agreement.

onboarding/Offer-Letter.html

☐  The candidate’s name and the acceptance deadline are filled in.

onboarding/Offer-Letter.html

☐  Non-solicitation period, termination notice and the arbitration-vs-courts question are decided; the non-compete clause is either removed or attorney-reviewed before it is signed.

onboarding/Employment-Agreement.html

☐  The Confidentiality & Data-Handling Agreement states the approved storage locations, the personal-device rule and the post-employment duration.

onboarding/Confidentiality-and-Data-Handling-Agreement.html

☐  All three documents are exported clean, with no TBD markers visible to the candidate.

3RD PRIORITY

## Publish the finalized set to Google Drive

The whole SOP and onboarding library, final and versioned, in the folder structure Sarah will actually use — with anything still open clearly flagged rather than silently left blank.

☐  The folder structure in the Internal Reference Sheet is confirmed by Sarah and built in Drive.

sops/Internal-Reference-Sheet.html

☐  Every document is exported to Drive in final form — PDF for anything signed or client-facing, editable for anything Sarah maintains.

☐  Documents with parked questions carry a visible ‘open item’ flag at the top, so the specialist never mistakes a gap for a rule.

☐  A single table of contents points to every document and states which are final and which are provisional.

☐  The stale OptiMind-SOPs-Export copy is retired, so there is only one live set.

4TH PRIORITY

## Week One onboarding support (Sep 8–12)

Everything in the Week-One Onboarding Schedule — pre-day-one provisioning through the Day 5 one-to-one — supported directly by Gemini Lane.

☐  Before day one: company email created with signature, Calendly seat with all four event types, calendar sync to Sarah, Zoom seat, document and client-file access granted, weekly one-to-one on the calendar.

sops/Week-One-Onboarding-Schedule.html

☐  Employment paperwork signed and filed before the first day, not during it.

☐  Day 1–5 run as written: Role Definition walkthrough, Client Workflow and curriculum training, provider-coordination templates, three mock sessions, documentation practice, first one-to-one.

sops/Week-One-Onboarding-Schedule.html

☐  Every account and tool the specialist needs in week one is confirmed working before Sep 8, not discovered missing on the day.

☐  A short end-of-week debrief records what the schedule got wrong, so week two is corrected rather than repeated.

5TH PRIORITY

## How-to capture for SOP documentation

Step-by-step visual guides recorded once while the work is being done — Scribe or equivalent — so the written SOPs are backed by something a new hire can follow click by click.

☐  A capture tool is selected — Scribe Pro Personal runs $25/seat/month annual, $35 monthly; the free tier is web-only with no desktop capture.

☐  The recurring tasks worth capturing are listed first: booking through Calendly, running a session in Zoom, filing a session note, updating the curriculum tracker, sending the teacher and therapist templates, invoicing.

sops/Client-Workflow-Intake-to-Graduation.html

☐  Each captured guide is exported and linked from the SOP document it belongs to, rather than living only inside the tool.

☐  A rule is written for who records a new guide when a process changes, so the library does not go stale the moment the engagement ends.

sops/Organization-and-Labeling-Standards.html

6TH PRIORITY

## Caseload ramp curve, weeks 1–8

Replace the placeholder ramp table in the Week-One Onboarding Schedule with the real week-by-week hour targets, agreed with Sarah.

☐  A target billable-hours figure exists for each of weeks 1 through 8, ending at the confirmed ~30 hours.

sops/Week-One-Onboarding-Schedule.html

☐  Which clients Sarah hands off, and in which week, is named against the curve rather than left to be worked out later.

☐  The curve accounts for the mock-session and shadowing weeks that carry no billable load.

☐  The Week-One Onboarding Schedule and the Role Definition both reflect the same numbers.

sops/Role-Definition-and-Responsibilities.html

7TH PRIORITY

## Client resource documents — inventory and draft the missing set

The Client Resources page lists twenty-five documents the specialist works from. Three of them exist. These are the forms and worksheets her caseload actually runs on.

☐  Every client resource document is inventoried against what actually exists — today 3 of 25 have a file behind them.

client-resources.html  ·  New-client set 12 documents, established-client set 11, plus the document-collection checklist.

☐  The New Client Intake Form is confirmed as the live version, and whether it serves all three client types or only adults.

forms/OptiMind-Adult-Intake-Form.html  ·  Filed under Adult, but listed as an all-client-types document — one of these is wrong.

☐  The Parent Accountability Contract is finalized alongside the Parent Terms of Service, rather than duplicating it.

sops/Parent-Terms-of-Service.html

☐  The rest of the all-client intake set is drafted: Time Account Spreadsheet, Client Set-up Sheet, Syllabus Form, School and Therapist Information Release Forms.

sops/Client-Workflow-Intake-to-Graduation.html  ·  The release forms gate every provider conversation — without them the Client Workflow stalls at stage two.

☐  The school-age set is drafted: School Info Form, Teacher Feedback Form, and the teacher and therapist email templates.

sops/Role-Definition-and-Responsibilities.html  ·  The Role Definition has the specialist using these templates from week one.

☐  The established-client worksheets are inventoried and prioritized by client type, with a target sprint against each.

client-resources.html  ·  Middle & high school 7, college 3, adult 1 — none drafted yet. Not all of these belong in Sprint 02.

☐  Every document that gets drafted is linked from the Client Resources page, so nothing exists only in a folder.

client-resources.html

Sprint 02 is done when All thirty-four boxes above are ticked, or the ones that are not carry a named owner and a date in a later sprint. The specialist has finished her first week against a written plan, and the debrief has been captured. There is exactly one live copy of the SOP and onboarding set, and it is in Sarah’s Drive.

Reviewed by ______________________________     Date ________________

OptiMind Educational Strategies · Sprint 02 of 12 · Generated from the live sprint board, 2026-08-31